## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 |  | 2025-10-08 | Backend state machine stuck after invalid DTMF | Sprint 2 | Backend | Maintainability | Added default fallback branch in state handler | 2025-10-09 | Closed | Resolved DTMF issue
2 |  | 2025-10-15 | Backend returns blank response for unknown state | Sprint 2 | Backend | Maintainability | Added standardized fallback response | 2025-10-16 | Closed | Resolved successfully
3 |  | 2025-10-22 | Voice input not triggering fallback response | Sprint 2 | Backend | Logical | Implemented fallback “Sorry, I didn't understand” handler | 2025-10-23 | Closed | improved triggering
4 |  | 2025-10-26 | Continuous speech restart error after stop | Sprint 2 | Frontend | Logical | Added async guard & interrupt flag | 2025-10-27 | Closed | Verified successfully
5 |  | 2025-11-01 | Invalid key mapping for voice utterance synonyms | Sprint 2 | Backend | Logical | Expanded voice-to-DTMF map | 2025-11-02 | Closed | Validated with correct key mapping
6 |  | 2025-11-05 | Speech recognition not stopping after ending the call | Sprint 3 | Frontend | Maintainability | Added explicit stop & state reset in onend | 2025-11-06 | Closed | Resolved the issue
7 |  | 2025-11-09 | UI keypad disabled incorrectly on refresh | Sprint 3 | Frontend | User Interface | Added conditional state restore on DOM load | 2025-11-10 | Closed | Verified successfully
8 |  | 2025-11-12 | Typing animation overlapping with voice output | Sprint 3 | Frontend | User Interface | Added stopTyping() before speak() | 2025-11-13 | Closed | modified the state change
9 |  | 2025-11-15 | Call duration counter continues after refresh | Sprint 3 | Frontend | User Interface | Added cleanup logic on unload | 2025-11-16 | Closed | Improved UI utility
10 |  | 2025-11-18 | Frontend fetch blocked by CORS | Sprint 4 | Backend | Maintainability | Enabled CORS in Flask middleware | 2025-11-19 | Closed | Resolved CORS issue

## Sheet2
Logical
User Interface
Maintainability
Standards
Others